## Sheet1
Procurement Process Planning Tool（Reference Template）
15-step standardized procurement timeline management for B2B customization
Step | Phase | Key Task | Responsible Party | Cycle (Days) | Start Date | End Date | Status | Remarks
1 | Demand Confirmation | Submit detailed procurement requirements | Client / Sales | 3
2 | Quotation Solution | Provide Tech Pack, formal quote & lead time | UniOuter | 3
3 | Contract Signing | Confirm terms, payment & delivery | Both Parties | 2
4 | Fabric Sourcing | Fabric selection, color swatch confirmation | Fabric Supplier | 7–15 |  |  | In-stock: 7 days
5 | Sampling | Initial sample & revised sample production | Factory | 7–10 |  |  | Expedited available
6 | Sample Approval | Client sealed sample confirmation | Both Parties | 2
7 | Bulk Material Preparation | Purchase fabric, accessories & logo crafts | Factory | 5–10
8 | Cutting | Pattern grading, fabric cutting & sorting | Factory | 2–3
9 | Sewing & Assembly | Garment stitching, taping & assembly | Factory | 7–15 |  |  | Complex style: longer
10 | Finishing | Ironing, trimming & final cleaning | Factory | 2
11 | Quality Inspection | Pre-inspection, inline inspection & final inspection | QC Team | 2–3 |  |  | Third-party inspection supported
12 | Packaging | Label attaching, folding & carton packing | Factory | 1–2
13 | Shipment | Customs declaration & logistics arrangement | Logistics Team | 3–7
14 | Goods Acceptance | Quantity & quality verification | Client | 2
15 | After-sales & Filing | Payment settlement & document archiving | Both Parties | 1
Notice:This template is provided for reference purposes only.Please formulate your work plan based on your own specific circumstances.